## High-Level Implementation
Step | Area | Action | Output | Owner | Priority | Dependency
1 | Governance | Define data ownership per domain | Domain ownership model | Data Office | High | None
2 | Governance | Define data standards (naming, schemas, contracts) | Data standards document | Data Office | High | Step 1
3 | Governance | Set up Collibra and onboard metadata sources | Central data catalog | Data Office / IT | High | Steps 1-2
4 | Platform | Identify priority domains (pilot) | Pilot scope defined | Architecture Team | High | Step 1
5 | Platform | Set up base ingestion patterns (batch, API, streaming) | Standard ingestion templates | Data Engineering | High | Step 4
6 | Platform | Define lakehouse structure (raw, standardized, curated) | Data model structure | Data Engineering | High | Step 5
7 | Data | Build first pipelines from core systems (SAP, Workday) | Initial datasets | Data Engineering | High | Steps 5-6
8 | Data | Define and publish first data products | Domain data products | Domain Teams | High | Step 7
9 | Data | Register data products in Collibra | Discoverable datasets | Domain + Governance | High | Steps 3, 8
10 | Integration | Define API and data sharing patterns | Integration standards | Architecture Team | High | Steps 2-5
11 | Applications | Refactor key dashboards to use data products | Standardized reporting | BI Teams | Medium | Steps 8-10
12 | Applications | Identify and remove duplicate datasets/pipelines | Reduced duplication | Domain Teams | Medium | Steps 8-11
13 | Platform | Enable cross-platform data access (Azure, AWS, SAP, Palantir) | Interoperability layer | Data Engineering | High | Steps 9-10
14 | Governance | Implement data quality rules | Data quality metrics | Governance + Domains | High | Steps 3, 8-9
15 | Enablement | Train teams on data products and standards | Upskilled teams | Data Office | Medium | Steps 2, 8
16 | Enablement | Establish community of practice | Adoption model | Data Office | Medium | Step 15
17 | Scale | Expand data products to all domains | Organization-wide coverage | All Domains | High | Steps 9, 13, 15
18 | Optimization | Optimize platform usage and costs | Reduced cost | IT / Architecture | Medium | Steps 13, 17
19 | Advanced | Introduce AI / advanced analytics use cases | AI solutions | Data Science Teams | Low | Steps 14, 17

## Detailed Implementation
Platform | Area | Action | Output | Owner | Dependency | Priority
Azure (Fabric / Lakehouse / Data Factory)
Azure (Fabric / Lakehouse / Data Factory) | Setup | Create workspace structure per domain | Domain isolation | Data Platform Team | Governance model approved | High
Azure (Fabric / Lakehouse / Data Factory) | Storage | Create lakehouse (raw / standardized / curated) | Data zones | Data Engineering | Setup | High
Azure (Fabric / Lakehouse / Data Factory) | Ingestion | Build pipelines (Data Factory / Fabric pipelines) | Data ingestion | Data Engineering | Storage | High
Azure (Fabric / Lakehouse / Data Factory) | Processing | Implement Spark transformations | Clean datasets | Data Engineering | Ingestion | High
Azure (Fabric / Lakehouse / Data Factory) | Modeling | Build semantic models (Fabric / Power BI) | Business-ready data | BI Engineering | Processing | Medium
Azure (Fabric / Lakehouse / Data Factory) | Data Products | Expose curated datasets | Reusable data products | Domain Data Teams | Modeling | High
Azure (Fabric / Lakehouse / Data Factory) | Access | Configure RBAC and domain access | Secure access | Security + Platform | Setup | High
Azure (Fabric / Lakehouse / Data Factory) | Integration | Enable API endpoints / connectors | Interoperability | Integration Team | Data Products | Medium
Azure (Fabric / Lakehouse / Data Factory) | Monitoring | Set up pipeline monitoring | Reliability | Data Platform Ops | Ingestion | Medium
AWS (S3 / Glue / Athena / EMR)
AWS (S3 / Glue / Athena / EMR) | Setup | Define S3 bucket structure (raw / processed / curated) | Data zones | Cloud Data Team | Governance standards | High
AWS (S3 / Glue / Athena / EMR) | Catalog | Configure Glue Data Catalog | Metadata | Cloud Data Team | Setup | High
AWS (S3 / Glue / Athena / EMR) | Ingestion | Build ingestion pipelines (Glue / Lambda) | Data ingestion | Data Engineering | Setup | High
AWS (S3 / Glue / Athena / EMR) | Processing | Use Spark (EMR / Glue jobs) | Transformations | Data Engineering | Ingestion | High
AWS (S3 / Glue / Athena / EMR) | Query | Enable Athena queries | Analytics access | Analytics Team | Catalog + Processing | Medium
AWS (S3 / Glue / Athena / EMR) | Data Products | Publish datasets via Glue / APIs | Reusable data | Domain Data Teams | Processing | High
AWS (S3 / Glue / Athena / EMR) | Security | Configure IAM roles | Access control | Security Team | Setup | High
AWS (S3 / Glue / Athena / EMR) | Integration | Enable cross-platform data exchange | Interoperability | Integration Team | Data Products | Medium
AWS (S3 / Glue / Athena / EMR) | Optimization | Optimize storage and queries | Cost efficiency | Cloud Platform Ops | Query usage baseline | Medium
SAP Datasphere
SAP Datasphere | Setup | Define business data models | Enterprise schema | SAP Data Team | Data standards | High
SAP Datasphere | Integration | Connect SAP systems (S/4HANA) | Data ingestion | SAP Integration Team | Setup | High
SAP Datasphere | Modeling | Create semantic models | Business logic layer | SAP Data Team | Integration | High
SAP Datasphere | Data Sharing | Expose datasets to external platforms | Interoperability | Integration Team | Modeling | Medium
SAP Datasphere | Governance | Align metadata with Collibra | Data visibility | Governance + SAP Team | Collibra onboarding | High
SAP Datasphere | Optimization | Reduce duplication with other platforms | Efficiency | Architecture + SAP Team | Data Sharing | Medium
Palantir Foundry
Palantir Foundry | Setup | Define ontology and data models | Business layer | Foundry Team | Domain ownership model | High
Palantir Foundry | Ingestion | Connect external datasets | Integrated data | Foundry Team | Setup | High
Palantir Foundry | Processing | Build pipelines (code / no-code) | Transformations | Foundry Team | Ingestion | High
Palantir Foundry | Applications | Build operational apps | Business tools | Product + Foundry Team | Processing | Medium
Palantir Foundry | Data Products | Expose datasets via ontology | Reusable assets | Foundry Team | Processing | High
Palantir Foundry | Integration | Sync with Azure / AWS datasets | Cross-platform use | Integration Team | Data Products | Medium
Palantir Foundry | Governance | Align with Collibra metadata | Visibility | Governance + Foundry Team | Collibra onboarding | High
Palantir Foundry | Optimization | Limit use to high-value use cases | Cost control | Architecture Board | Usage monitoring | Medium
Governance Layer (Collibra)
Governance Layer (Collibra) | Setup | Configure Collibra platform | Governance base | Data Governance Team | Ownership + standards | High
Governance Layer (Collibra) | Metadata | Ingest metadata from all platforms | Unified catalog | Data Governance Team | Setup | High
Governance Layer (Collibra) | Catalog | Build searchable data catalog | Discoverability | Data Governance Team | Metadata | High
Governance Layer (Collibra) | Lineage | Enable lineage tracking | Transparency | Data Governance Team | Metadata pipelines | High
Governance Layer (Collibra) | Ownership | Assign data owners per domain | Accountability | Data Office | Governance model | High
Governance Layer (Collibra) | Policies | Define governance rules | Compliance | Governance Council | Ownership | High
Governance Layer (Collibra) | Quality | Define data quality metrics | Trust | Governance + Domains | Policies | High
Governance Layer (Collibra) | Integration | Connect Azure, AWS, SAP, Palantir | Full visibility | Data Governance + IT | Metadata connectors | High
Cross-Platform Integration
Cross-Platform Integration | Standards | Define data contracts and schemas | Interoperability | Architecture Team | Data standards | High
Cross-Platform Integration | APIs | Build API layer for data access | Reusable services | Integration Team | Standards | High
Cross-Platform Integration | Data Sharing | Enable cross-cloud data exchange | Unified data | Integration Team | APIs | High
Cross-Platform Integration | Synchronization | Align datasets across platforms | Consistency | Data Engineering | Data Sharing | Medium
Cross-Platform Integration | Governance | Ensure all shared data is cataloged | Control | Governance Team | Collibra integration | High
Data Products
Data Products | Definition | Define data product template | Standardization | Data Office | Data standards | High
Data Products | Ownership | Assign domain owners | Accountability | Domain Leads | Definition | High
Data Products | Development | Build domain datasets | Data products | Domain Data Teams | Ownership | High
Data Products | Exposure | Publish via APIs/catalog | Discoverability | Domain Teams + Governance | Development | High
Data Products | Reuse | Enable cross-domain usage | Efficiency | Architecture + Domain Teams | Exposure | Medium
Applications & BI
Applications & BI | BI | Connect Power BI / Tableau to data products | Reporting | BI Teams | Data products exposed | High
Applications & BI | Apps | Build apps using APIs and datasets | Operations | App Teams | API layer available | Medium
Applications & BI | Standardization | Reduce duplicated dashboards | Consistency | BI Governance | BI onboarding | Medium
Applications & BI | Migration | Refactor legacy dashboards | Optimization | BI Teams | Standardization | Medium
Enablement
Enablement | Training | Train teams on data products | Capability | Data Office | Initial data products | High
Enablement | Guidelines | Define best practices | Consistency | Architecture + Governance | Training plan | Medium
Enablement | Community | Create data community | Adoption | Data Office | Guidelines | Medium
Enablement | Support | Provide platform support | Sustainability | Platform Ops | Community launch | Medium

## KPIs
KPI ID | KPI Category | KPI Name | Definition | Formula | Baseline | Target | Measurement Frequency | Owner | Data Source | Status
KPI-01 | Governance | Data Ownership Coverage | % of critical datasets with assigned owner | Owned critical datasets / total critical datasets | 0% | 100% | Monthly | Data Office | Collibra | Not Started
KPI-02 | Governance | Metadata Completeness | % of catalog entries with required metadata fields | Complete entries / total catalog entries | TBD | >=95% | Monthly | Governance Team | Collibra | Not Started
KPI-03 | Quality | Data Quality Pass Rate | % of quality checks passing | Passed checks / total checks | TBD | >=98% | Weekly | Governance + Domains | DQ Rules Engine | Not Started
KPI-04 | Platform | Pipeline Success Rate | % of successful pipeline runs | Successful runs / total runs | TBD | >=99% | Daily | Data Engineering | Azure/AWS Monitoring | Not Started
KPI-05 | Platform | Ingestion Lead Time | Time to onboard a new source to production | Avg days from request to go-live | TBD | < 14 days | Monthly | Data Engineering | Delivery Tracker | Not Started
KPI-06 | Data Products | Published Data Products | Count of production-grade data products | Number of active data products | 0 | >=25 | Monthly | Domain Teams | Catalog + API Registry | Not Started
KPI-07 | Adoption | Data Product Reuse Rate | % of products consumed by 2+ teams | Reusable products / total products | TBD | >=60% | Quarterly | Architecture Team | Access Logs | Not Started
KPI-08 | Applications | Dashboard Standardization | % of dashboards powered by approved data products | Standardized dashboards / total dashboards | TBD | >=80% | Monthly | BI Teams | BI Inventory | Not Started
KPI-09 | Integration | Cross-Platform Exchange Coverage | % of priority cross-platform use cases enabled | Enabled use cases / planned use cases | TBD | >=90% | Monthly | Integration Team | Integration Backlog | Not Started
KPI-10 | Cost | Data Platform Unit Cost | Cost per TB processed/stored | Total platform cost / TB processed | TBD | -20% vs baseline | Monthly | IT / Architecture | Cloud Cost Reports | Not Started
KPI-11 | Enablement | Training Completion Rate | % of target users completed training | Completed users / target users | 0% | >=90% | Monthly | Data Office | LMS | Not Started
KPI-12 | Advanced Analytics | AI Use Cases in Production | Number of AI/ML use cases in production | Count of active AI use cases | 0 | >=5 | Quarterly | Data Science Teams | AI Portfolio | Not Started